## Sheet2
Special Programme for Development Infrastructure
No | GN Division | Project Proposal | Allocation | Estimated Amount | Agrement Amount | Financial Progress | පරිපාලන වියදම | Current Status
1 | Kohunugamuwa | Development of the by road in Samagi Mawatha | 500000 | 499997.92 |  | 457663.62 |  | Completed
2 | Kohunugamuwa | Development of Geriatahena Road | 500000 | 499983.9 |  | 495033.57 |  | Completed
3 | New Street | Construction of drainage system at WeligamaNew Street Palalla Road 2 nd Stage | 500000 | 499851.55 |  | 494902.52 |  | Completed
4 | Kapparathota North | Obtain Body Building kits for registration Sports clubs /Youth Clubs | 500000 | 500000 |  | 494730 |  | Completed
5 | Pelena West | Obtain Body Building kits for registration Sports clubs /Youth Clubs | 500000 | 500000 |  | 495000 |  | Completed
6 | Galbokka south & West | Obtain Body Building kits for registration Sports clubs /Youth Clubs | 500000 | 500000 |  | 495000 |  | Completed
7 | Walliwala South | Distribute Sports item/ Body Building machines for Gamuni Sports club | 500000 | 500000 |  | 494970 |  | Completed
8 | Walliwala West | Improvement of the sanitary facilities of Mr/Jinarathna School | 500000 |  |  |  |  | Astimated
9 | Walliwala East | Development of Municipal counsil area of Weligama old Galle Harbour of Walliwala east and development of by road to Sewanagahalaga | 500000 |  |  |  |  | Amendments have been requested
10 | Main Street | Development of 1 st by road to Jayawickrama | 500000 | 499861.35 |  | 489875.38 |  | Completed
11 | Kotawila South | Obtain sports equipments/ body building equipment to Gamunu sports club | 500000 | 500000 |  | 495000 |  | Completed
12 | Kamburugamuwa | Obtain sports equipments/ body building equipment to Gamunu sports club | 500000 |  |  | 495000 |  | Completed
13 | Mirissa Udupila | Obtain sports equipments/ body building equipment to Suhada sports club, Udupila Mirissa | 500000 | 500000 |  | 494930 |  | Completed
14 | කප්පරතොට දකුන |  | 500000 | 499988.12 |  |  |  | Completed
14 | Kapparathota South | Modernization of Primary Health Center | 500000 | 499988.12 |  | 495037.74 |  | Completed
|  |  | 7000000 | 5499682.84 |  | 5897142.83

## Sheet3
වැලිගම ප්‍රාදේශිය ලේකම් කොට්ඨාශය
ග්‍රාමීය යටිතල පහසුකම් සංවර්ධන විශේෂ වැඩසටහන - 2018
2018.12.31 දිනට ක්‍රියාත්මක නොවු ව්‍යාපෘති
අනු අං. | ග්‍රාම නිලධාරී වසම | ව්‍යාපෘති යෝජනාව | වෙන් කරන | ඇස්තමේන්තු මුදල | ගිවිසුම් ගත මුදල | මුල්‍ය ප්‍රගතිය | පරිපාලන වියදම
ප්‍රතිපාදන රු.
8 | වල්ලිවල බටහිර | මාර/ ජිනරතන පාසලේ සනීපාරක්ෂක පහසුකම් වැඩි දියුණු කිරිම | 500000
9 | වල්ලිවල නැගනහිර | වැලිගම නගර සභා බල ප්‍රදේශයවල්ලිවල නැගනහිර පරණ ගාලු වර‍ාය සෙවන ගහ ලග වැටෙන අතුරු මාර්ගය සංවර්ධනය කිරිම | 500000
|  |  | 1000000 | 0 |  | 0